## Sheet1
Bonne Femme Watershed Project Cost-Share Applications
Name | date submitted (signed date of application) | date visited | contract date | Project | Recommendation | estimated cost (including match) | Comments | Subwatershed ranking
McCarty | 2006-03-06 | 2006-06-07 |  | septic pumpout, runoff from neighboring construction site
Harman | 2006-06-04 | 2006-06-22 |  | streambank stabilization | put a pickup-load of 6" rock in the field gulley to stop its growth
Hayes | 2006-05-29 | 2006-06-06 |  | streambank stabilization | let it grow up in trees | 0 | recommend they apply for NRCS' riparian CRP
Davison | 2006-05-08 | 2006-06-06 |  | streambank stabilization | quit mowing under trees in riparian area | 0
Sims | 2006-05-05 | 2006-06-05 |  | streambank stabilization | 4 sites (60'-100' each) with either rock or cedar tree revetements | $7,000-10,000 | seems reluctant to establish riparian area
Dickerson | 2006-05-04 | 2006-06-05 |  | streambank stabilization | quit mowing under trees in riparian area | 0
Buster | 2006-05-04 | 2006-07-18 |  | streambank stabilization | a few gully plugs needed; probably too inexpensive to fund |  | haven't been able to get ahold of them
Foriester | 2006-05-04 | 2006-06-22 |  | streambank stabilization | expand riparian corridor, don’t let power company cut down more trees
Knipp | 2006-05-05 |  |  | streambank stabilization
Sims | 2005-03-09 | 2006-03-27 |  | lake | not funding lake because there is not water quality benefit (would control runoff from rural property, thereby altering the natural hydrology) |  | wants to build a large lake between his house and the creek
Smith | 2006-03-13 | 2006-03-24 |  | rain garden, rain barrels | fund both | $400-800
Huffman | 2006-05-23 | 2006-06-14 |  | control flooding, streambank stabil. | streambank looks ok, will consider rain gardens (gone for summer), wants to do other berming
Stevens | 2006-04-22 |  | 2006-04-21 | septic pumpout, septic repair | fund pumpout, can't fund repair because application submitted after work completed | 125
Cook | 2006-04-19 | 2006-05-25 |  | sinkhole cleanout/reveg. |  |  | too much vegetation for a good evaluation; will look at it again after the foliage is down
Rice | 2006-05-03 | 2006-05-12 |  | dump removal, ditch stabilization |  |  | delayed due to lack of funds
Roberson | 2006-03-21 | 2006-03-24 |  | re-contour & revegetate borrow pit, build lake | approved |  | need more info re: cost
Hagans | 2006-03-15 | 2006-03-24 |  | re-do pond so it captures drainage, fence out cattle, install frost-proof waterer | worthy practice, refered to NRCS |  | Kevin Moncton stated that he is on list to receive cost-share, probably in 2007
Langdon/Comm. Garden Coalition | 2006-04-04 | 2006-02-01 |  | rain garden at New Haven Elementary | worthy of funding |  | Ms. Langdon realized she did not have all her ducks in a row, will look into it for fall 2006
Squires | 2006-06-07 | 2006-06-14 | 5/16/2007 authorized pumping (pumped 6-7-07) | Septic pumpout | on the cusp of needing it, will call me again in the spring | 100 | re-visited on 5/16/07, approved pumping
Grace | 2006-06-11 | 2006-06-19 | 7/31/06 authorized payment | Septic pumpout | needs pumping | 100
Radel | 2006-06-19 | 2006-07-18 |  | streambank stabilization | several large banks need stabilization along LBF | $24,000-36,000
Windmiller | 2006-06-22 | 2006-07-18 |  | streambank stabilization | one medium bank needs stabiliz. To protect shed | 7500 | withdrew application because she couldn't find people to do the work for a reasonable amount
Diggs | 2006-06-21 | 2006-07-18 |  | onsite sewer upgrade | staff recommends approval, pending cost-estimates |  | located on Log Providence Rd.; on 6/23/06, said they would send in an application
Strothman |  |  |  | potential LID subdivision |  |  | developer for 35 ac. On Rt. K, next to RBMSP; have another meeting set up with their engineer; developer sold property
Chris Davis |  |  |  | upgrade of detention basins |  |  | Forest Park South (Rock Quarry Rd.) developer, has detention that could be modified for ~$10k
Griggs | 2006-06-24 |  |  | streambank stabilization
Potter |  | 2006-07-18 |  | septic pumpout | needs pumping
Idle | 2006-08-29 |  |  | septic pumpout | withdrew application
Darrow | 2006-08-29 | 2006-09-12 | 10/12/06 authorized payment | septic pumpout | needs pumping
Remeika | 2006-09-05 | 2006-09-08 |  | septic pumpout | doesn't need pumping quite yet
Hedglin | 2006-09-05 | 2006-09-20 | 10/10/06 authorized payment | septic pumpout | needs pumping
Stancil | 2006-09-03 | 2006-09-26 |  | septic pumpout | needs pumping (never pumped)
Pugsley | 2006-09-11 | 2006-09-20 |  | septic pumpout | doesn't need pumping quite yet
UM/Disc Ridge | 2007-04-19 |  |  | potential LID development | needs lots of clarification on their application |  | As of 3/16/07, no MOU, no application submitted. Mailed them letter on 3/13/07
Hayes | 2006-09-26 |  |  | gulley erosion
Hunt |  | 2006-09-29 |  | septic pumpout | doesn't need pumping quite yet
Houseworth | 2006-10-04 | ----- | 2006-12-26 | onsite sewer upgrade | approve | 22345
Piper | 2006-10-04 | 2006-10-06 | 10/9/06 authorized payment | septic pumpout | desperately needs pumping
Woods | 2006-10-05 | 2006-10-06 | 10/26/06 authorized payment | septic pumpout | needs pumping (18 years)
Pullen | 2007-02-26 | -------- | 2007-05-29 | onsite sewer upgrade | approve upgrade | 15800
UMC-Tindall | 2006-03-13 | -------- |  | rain garden | approve |  | pulled out at the last minute (final draft of contract prepared) because of 15-year maintenance requirement
RBHS |  |  |  | rain garden + level spreader in detention basin | approve
Cheavens | 2006-12-26 | 2007-03-05 |  | septic system cleaning, stream bank stabilization, fence cattle out/frost-free waterer
Holman | 2007-05-01 | 2007-05-23 | 5/23/07 authorized pumping | septic pumpout | needs pumping
Johnson (Will) | 2007-04-17 | 2007-05-15 |  | streambank stabilization & gulley plug | needs work
Blakemore | 2007-04-25 | 2007-05-15 |  | streambank stabilization | needs work
MDC/Bennett |  |  |  | wetland restoration in 3Creeks
Stephenson | 2007-04-26 |  |  | onsite sewer upgrade |  | $12-13,000
Crowley | 2007-06-08 | 2007-06-08 |  | streambank stabilization